## Sheet1 - Table 1 - Table 1 - Ta
Project name: Paint |  | Team number and members: 104 (Kyle Harris & L. Preston Sego III)
Stage | What the program will do | How we plan to test it | expected completion date | actual completion date
1 | Create View Windows | Run | 2008-03-30 | 2008-03-30
2 | Add basic pencil tool | see if we can draw | 2008-03-30 | 2008-03-30
3 | Add Paint Brush tool | see if we can draw thicker than pencil | 2008-04-09 | 2008-04-09
4 | Have User choose-able Canvas size | Make different sized windows | 2008-04-09 | 2008-04-09
5 | Have buttons from their own separate window talk to the canvas | See if we can choose different tools to draw with | 2008-04-09 | 2008-04-09
6 | Color Options | change colors
7 | Color Text Entry Boxes | Color appears in color preview box
8 | Add Other tools | Draw with different sizes, shapes, etc
9 | Ability to Erase part of the picture | Erase Things
10 | Draw Shapes | draw shapes
11 | Text Entry | Type
12 | Maybe Import Images | Load
13 | Save the image | Be able to convert the canvas to an image, save, open in a REAL image editor, and load again from our own paint program
14
15
16
17
18
19
20
21