## Sheet1 - Table 1 - Table 1 - Ta
Project name: Paint |  | Team number and members: 104 (Kyle Harris & L. Preston Sego III)
Stage | What the program will do | How we plan to test it | expected completion date | actual completion date
1 | Create View Windows | Run the program and see if the windows show up properly. | 2008-03-30 | 2008-03-30
2 | Add basic pencil tool | Attempt to use the tool and see if it draws to the canvas correctly. | 2008-03-30 | 2008-03-30
3 | Add Paint Brush tool | Attempt to use the tool and see if it draws to the canvas correctly. | 2008-04-09 | 2008-04-09
4 | Have User choose-able Canvas size | Run the program and see if the windows display and the canvas displays as the inputed size. | 2008-04-09 | 2008-04-09
5 | Have buttons from their own separate window talk to the canvas | See if we can choose different tools to draw with by clicking on the buttons in the tool window. | 2008-04-09 | 2008-04-09
6 | Color Options window | Display a color option window that will change the color being drawn with any given tool on the canvas. | 2008-04-13 | 2008-04-10
7 | Color Text Entry Boxes | Color appears in color preview box. EDIT: rendered unnecessary with the JColorChooser, it has a preview built in. | 2008-04-13 | N/A
8 | Add Rectangle and Oval drawers. | Run the program and see if Rectangles and Ovals can be drawn properly. | Apr, 13 2008 | Apr, 11 2008
9 | Ability to Erase part of the picture | Erase Things | Apr, 13 2008 | Apr, 11 2008
10 | Implement Polygon drawer | Run the program and see if polygons can be drawn by left-clicking for new points and right clicking to complete the polygon. | Apr, 13 2008 | Apr, 11 2008
11 | Add menu bar | Check to see if a menu bar appears in the canvas window when the program runs. EDIT: we had to adjust the canvas size setter to make sure the images were the correct size after we implemented this. | Apr, 13 2008 | Apr, 11 2008
12 | Add show and hide color window options to the menu | See if the color chooser menu can be hidden and pulled back to the top using the menu opton bar. | Apr, 13 2008 | Apr, 12 2008
13 | Import Images | Load images to the canvas and then be able to draw over and on the images. | Apr, 13 2008 | Apr, 12 2008
14 | Save the image | Be able to save the image, then load it and see if it is indeed, the exact image we saved. EDIT: The save works, but if it's done in windows, and the actual save screen overlaps the canvas screen, that is saved on top. This is because our save involves a screen capture. | Apr, 13 2008 | Apr, 13 2008 Kind of.
15
16
17
18
19
20
21
22