## Sheet1
Project name: Paint |  | Team number and members: Jinwoo Baek, Michael Crane, 110
Stage | What the program will do | How we plan to test it | expected completion date | actual completion date
1 | Have a Frame with three components | We will open it and see | April 7th 2008 | April 7th 2008
2 | Have the components in the right place | We will open it and see | April 7th 2008 | April 7th 2008
3 | Put all the Buttons with the right label on it | We will open it and see | April 7th 2008 | April 7th 2008
4 | Put all the right colors in the color choosing component | We will open it and see | April 7th 2008 | April 8th 2008
5 | Make sure all panels show in right size | We will open it and see | April 8th 2008 | April 8th 2008
6 | Make sure the buttons on the tools buttons panel show in right size | We will open it and see | April 11th 2008 | April 11th 2008
7 | Make sure all the buttons in color choosing component to show in right size | We will open it and see | April 11th 2008 | April 11th 2008
8 | Make the connection between the three panels | By seeing if the color changing buttons in Tools panel would affect the color of the background in drawing panel. This could be also done between Colorselection panel with Drawing panel. | April 11th 2008 | April 12th 2008
9 | implement the MouseListener, ActionListener, MouseMotionListener in the drawing Panel. Also, make sure the paintComponent works using Swing code from before | use the swing code and check | April 11th 2008 | April 13th 2008
10 | Write out algorithm for two tools buttons | See if the tools show up in drawing in the drawing panel | April 12th 2008 | April 13th 2008
11 | Wirte out all the algorithms for pencil, brush, rectangle, and circle | Check by looking at the drawing panel | April 12th 2008 | April 13th 2008
12 | Put in the algorithm so that we can involve the affect of changing colors | We can check by checking the drawing panel | April 12th 2008 | April 13th 2008
13 | Wirte out the algorithm for polygon | Check by looking at the drawing panel | April 12th 2008 | April 14th 2008
14 | Put a new panel in the frame for the selection of different kinds of brush. | Check by looking at the frame and drawing the brush with different size and kind in the drawing panel. | April 13th 2008 | April 14th 2008
15 | Write all Javadoc | look at the Javadoc | April 13th 2008 | April 14th 2008
16 | Make sure everthing works together. | run the program and try different things | April 13th 2008 | April 14th 2008
17 | If time permits write "clear image" function | check if the function works by drawing stuff in the drawing panel then clicking on the clear image button | April 14th 2008 | April 14th 2008
18 | If time permits write "open/save/new" function | check by trying all these functions | April 14th 2008 | April 14th 2008
19 | If time permits write "spray paint" function | check by drawing in the drawing panel | April 14th 2008 | April 14th 2008
20 | If time permits write "undo" function | check by drawing in the drawing panel and undo. | April 14th 2008 | April 14th 2008