## Sheet1
Project name: Paint |  | Team number and members: 101 Bryce B. Casimir K.
Stage | What the program will do | How we plan to test it | expected completion date | actual completion date | Comments
1 | Get frame/ panels/ buttons to appear | Run and look | 2008-03-29 | 2008-03-28
2 | Brush and Pencil Functionality | Run and draw somelines and squiggles | 2008-03-30 | 2008-03-29
3 | Rectangle and Circle Functionality | Run and draw some of each | 2008-03-30 | 2008-03-29
4 | Polygon Functionality | Run and draw some of polygons | 2008-03-30 | 2008-04-09 | More involved then originally thought.
5 | Allow Color Selection | Draw items with different all colors | 2008-03-31 | 2008-03-29
6 | Paint Bucket Funtionality | Draw closed shapes and fill with paint bucket | 2008-04-03 | --- | Do not need to implement
7 | Shift constrains rectangles to squares and ovals to circles | Draw some squares and circles using shift constraint | 2008-04-04 | 2008-04-05
8 | Enable Eraser | Use eraser to delete stuff | 2008-04-05 | 2008-03-30
9 | Spray Paint Functionality | Run and spray paint | 2008-04-06 | 2008-04-06
10 | Undo Command Functionality | Draw shapes and test to see if you can undo them | 2008-04-08 | 2008-04-05
11 | Menu bar including: Open, Save, New, Image | Run and test each Menu button | 2008-04-09 | --- | Decided not to implement, time constraint.
12 | Ability to move areas of the board | Test grabbing areas and moving them | 2008-04-11 | --- | Decided not to implement, time constraint.
13 | Get the brush tool to draw more smoothly using stroke | Draw with brush and try different brush sizes | 2008-04-11 | 2008-04-10 | Stroke slows down paint!!
14 | Set color sliders that allow for the user to select their colors. | Run the program and play with different colors | 2008-04-12 | 2008-04-13 | Also decided to remove color buttons from paint.
15 | Have a drawing preview in the bottom left corner. | Run and test all drawing tools so that they display | 2008-04-12 | 2008-04-12
16 | Add a documentation panel that comes up with paint. | Run and make sure the documentation comes up. | 2008-04-14 | 2008-04-14