## Sheet1
Project name: |  | Team number and members: 102 | Pete Brousalis | Ricky Chelminski
Stage | What the program will do | How we plan to test it | expected completion date | actual completion date
1 | Display a whiteboard where a pencil can be drawn once a mouse is pressed down. | Run the pencil test, draw Peter in the pencil. | April 5th | April 7th | Took a while because of personal issues to get done, but finished.
2 | Have the following shapes: Rectangle, polygon, oval/circle, able to drawn onto the canvas. | Draw the shapes overlapping eachother. | April 6th | April 14th | Polygon was much more difficult than we had planned it to be.
3 | Color each object before it is drawn using JColorSwatch. | Change the colors before the shapes are drawn. Make sure each object keeps its color | April 9th | April 9th
4 | Be able to clear the board, and fill the background of the board with color using JColorSwatch | Create the buttons and click each one. | April 11th | April 9th | Found once Stage 3 was finished, was very esay
5 | Display menu/buttons for aesthetically pleasing GUI. Tool buttons on top, swatches on left. File menu on top | Click buttons and menus to make sure they work. | April 13th | April 12th
6 | Text tool which when you click on canvas, are able to type and display text. Handle text with KeyListener | Click on canvas and display typed texted | April 14th | April 14th
7 | Set width of the brush by using a Jslider | Change the Jslider values to see if brush will change | April 15th | April 14th | Using a late day for final changes
8 | Make final adjustments/polish. No warnings/errors. | Make it an A worthy project! | April 15th | April 15th
9 | Save the current canvas as an image | Save the file as image.jpg. | April 15th
10
11
12
13
14
15