## Sheet1
Project name: Paint |  | Team number and members: 103 Annmarie Stanley, Hannah Chadd
Stage | What the program will do | How we plan to test it | expected completion date | actual completion date | Comments
1 | Display frame with title and panels in correct position | Run the program | 2008-04-07 | 2008-04-05
2 | Display buttons correctly | Run the program | 2008-04-07 | 2008-04-05
3 | Pencil tool works; drawing shows up in the window when the tool is clicked and drawn | Run the program and attempt to draw with the pencil | 2008-04-08 | 2008-04-14
4 | Brush tool works; drawing shows up in the window as expected | Run the program and attempt to draw with the brush | 2008-04-09 | 2008-04-14
5 | Change colors when the appropriate buttons are clicked | Run the program, click on colors and attempt to draw | 2008-04-10 | 2008-04-10
6 | Rectangle draw tool works | Select the rectangle draw button and then click and drag the mouse to draw a rectangle | 2008-04-11 | 2008-04-09
7 | Oval/Circle draw tool works | Select the oval/circle draw button and then click and drag the mouse to draw an oval or a circle | 2008-04-11 | 2008-04-09
8 | Polygon draw tool works | Select the polygon draw button and click several times to establish the vertices of the polygon | 2008-04-12 | 2008-04-14 | Draws an extra line but does draw the polygons
9 | Paint bucket fill method works only for areas drawn with the polygon, circle/oval, and rectangle draw tools | Select the paint bucket and click inside a rectangle, circle/oval, or polygon | 2008-04-13 | Not attempted
10 | Paint bucket fill method works for all areas | Select the paint bucket and click inside a freely drawn area | 2008-04-13 | Not attempted
11 | File menu appears without functionality | Run the program | 2008-04-14 | 2008-04-13
12 | File menu appears and has working options to open, save and create a new file | Click on the menu and save a file, open one, and create a new one | 2008-04-15 | 2008-04-14 | Limited functionality; added a Help menu
13
14
15