## Sheet1
Project name: | Paint | Team Members Names: | Joe Wanstrath, Dillon Hunt
Stage | What the program will do | How we plan to test it | expected completion date | actual completion date
1 | Aligned GUI with panels and frames in place | GUI test | 2008-04-06 | 2008-04-06
2 | Working Canvas Panel | GUI test | 2008-04-06 | 2008-04-11 | partially done 4/10/08
3 | Implement Tool interface and Line Tool | GUI test | 2008-04-07 | 2008-04-08
4 | Implement Rectangle and Oval Tools | GUI test, console out of variables | 2008-04-07 | 2008-04-07 | couldn’t get the shift key listener working to create squares and circles
5 | Paint Bucket and Colorbar | GUI test | 2008-04-07 | 2008-04-08 | Paint Bucket is optional and removed from paint
6 | Paintbrush and Pencil | GUI test | 2008-04-08 | April 14,2008 | due to problems with the shape array, this was fixed late
7 | Polygon and Eraser | GUI test | 2008-04-08 | 2008-04-10
8 | Spraycan | GUI test | 2008-04-08 | April 14,2008 | optional, may be done by April 15
9 | SelectorBox and Text Tools | GUI test | 2008-04-09 | 2008-04-11 | Selector box removed from program; text finished
10 | Menu Bar that has File, Edit and Help (not necessarily functional) | GUI test | 2008-04-09 | 2008-04-14 | designed
11 | Finish Functionality of File menu | GUI test | 2008-04-10 | 2008-04-14 | functionality finished
12 | Final testing and revisions |  | 2008-04-14 |  | no save function. New, undo,redo,help all work