## Sheet1
Project name: |  | Team number and members:
Stage | What the program will do | How we plan to test it | expected completion date | actual completion date
1 | make a GUI that can draw using pencil tool | by drawing things | 2008-04-08
2 | add panel with different tools | click tools and test their functionality | 2008-04-10 | 2008-04-10
3 | add panel with multiple colors | use the different colors to draw things | 2008-04-12 | 2008-04-08
4 | implement brush tool | check to see if brush tool draws the correct size and ensure that it doesn't draw jagged shapes | 2008-04-12 | 2008-04-15
| implement fill tool | make multiple shapes and try filling them, checking to see if the paint spreads to the whole shape | 2008-04-14 | 2008-04-14
| implement line tool | compare with actual paint line tool by drawing lines onscreen | 2008-04-14 | 2008-04-13
5 | implement oval, rectangle, and rounded rectangle tools | compare with actual paint line tool by drawing shapes onscreen | 2008-04-16 | 2008-04-14
6 | add menu bar with save, open, image resize, and other various tools | try to open and save .png files, invert colors, and toggle the undo/redo buttons | 2008-04-12 | 2008-04-15
7 | correctly create frame with buttons placed in right spot | Run the program, compare button and frame positions to actual paint program | 2008-04-14 | 2008-04-11
8
9