## Sheet1
Project name: | Paint | Team number and members: 107 Jacob Wise and Eric Schulte
Stage | What the program will do | How we plan to test it | expected completion date | actual completion date
1 | Display a Window with a menu with limited functionality. | Run the program and use the menu. | 2008-04-07 | 2008-04-07
2 | Display a side panel that will have various icons on it. | Run the program and see if the panel shows up. | 2008-04-08 | 2008-04-08
3 | Displays a bottom panel that will have color options. | Run the program and see if the panel shows up. | 2008-04-08 | 2008-04-08
4 | Draws with a pencil. | Run the program and attempt to use pencil tool. | 2008-04-11 | 2008-04-12
5 | Draws with a paint brush. | Run the program and attempt to use paint brush tool. | 2008-04-11 | 2008-04-13
6 | Ability to choose different colors. | Run the program and try selecting different colors. | 2008-04-12 | 2008-04-11
7 | Draws shapes: rectangles, polygons, ovals. | Run the program and draw a couple of different shapes. | 2008-04-13 | 2008-04-13
8 | Draws rectangles and ovals filled with current color. | Run the program and try drawing filled rectangles and ovals. | 2008-04-13
9 | Ability to erase areas of the board | Run the program and attempt to use eraser tool. | 2008-04-14 | 2008-04-13
10 | Ability to use spray can tool | Run the program and attempt to use spray can tool. | 2008-04-12 | 2008-04-13