## Sheet1
Project name: Paint |  | Team number and members: Rich Stover, Mark Swanson
Stage | What the program will do | How we plan to test it | expected completion date | actual completion date
1 | Display a frame with a proper name to be used for Paint | Run the program and make sure it looks good | 2008-04-08 | 2008-04-08
2 | Display a canvas that will later be used to draw on (just a black sheet for now) | Run the program and make sure it displays the black sheet | 2008-04-08 | 2008-04-08
3 | Display a tool button panel, with the appropriate number of buttons | Run the program and look at the tool buttons | 2008-04-08 | 2008-04-08
4 | Display a color button panel, with appropraite number of buttons | Run the program and count the number of buttons to be used for colors | 2008-04-08 | 2008-04-08
5 | Make the buttons in color button panel have appropriate colors | Run program and look at color buttons | 2008-04-09 | 2008-04-08
6 | Make buttons in tool panel have titles showing their particular tool | Run program and look at tool panel | 2008-04-09 | 2008-04-08
7 | Display foreground/background buttons to later be used to show currently selected colors | Run program and look for buttons/titles | 2008-04-09 | 2008-04-08 | this was replaced by JColorChooser
8 | Give user ability to draw freeform with a pencil and brush | Run program and draw with both brush and pencil | 2008-04-09 | 2008-04-13 | no gaps for any object being drawn
9 | Add communication between panels | Run program and interact with one panel, but have another panel print a sysout | N/A (not initially thought of) | 2008-04-09 | cause of things completed on 11-Apr instead of 10-Apr
10 | Give user ability to select specific brush sizes in display panel | Run program and select specific brush sizes | 2008-04-10 | 2008-04-14 | can either use slider or mouse wheel to choose stroke size and spray density (with Ctrl)
11 | Give user ability to select a specific color | Run program and change colors, then draw | 2008-04-10 | 2008-04-11 | replaced by JColorChooser
12 | Give user ability to draw rectangles, circles/ovals, lines, and polygons | Run program and test rectangles, circles/ovals, and lines | 2008-04-10 | 2008-04-11 | all basic draw functions
13 | Give user ability to see a preview of where the shape will be if made at current mouse location | Run program and see preview of all shapes, as mouse is being moved | 2008-04-12 | 2008-04-12
14 | Give user ability to draw with a spray can | Run program and test the spray can | 2008-04-11 | 2008-04-11 | working, but too much spraycan will slow down program
15 | Add ability to use paint bucket (fill in enclosed area) | Run program and try to use the paint bucket | 2008-04-11 |  | since project specs have this tool changed to option, may not implement
16 | Make it possible to use the shift key to restrain rectangle to square, and oval to circle | Run program and hold shift key while making rectangles and ovals | 2008-04-12 | 2008-04-14 | works perfect
17 | Display a color display panel, which will be used to display the currently selected color | Run the program and look at panel | 2008-04-12 | 2008-04-11 | replaced by JColorChooser
18 | Make the color display panel show currently selected color | Run program and make sure currently displayed color matches | 2008-04-12 | 2008-04-11 | replaced by JColorChooser
19 | Add undo/redo to edit menu, add clear image | Run program, draw several objects and undo individual objects, then redo them and clear all |  | 2008-04-14 | undo and clear image and redo all work
20 | Add a File Menu in order to open/save/new. | Run program, make new file, save file, open file | 2008-04-13 | 2008-04-13 | new file not implemented, save file works perfect, and open file works perfectly
21 | Add an Image Menu in order to flip/rotate, invert colors, and attributes frame | Run program and flip/rotate, invert colors, and look at the attributes | 2008-04-13 | 2008-04-13 | decided to just do clear image