## Sheet1
Project name: Paint |  | Team number and members: 111, Matt Drosos and Colin DeClue
Stage | What the program will do | How we plan to test it | expected completion date | actual completion date
1 | have buttons on the panel and a blank white space | Run the program and look | 2008-04-07 | 2008-04-09
2 | pencil works | Run the program and look | 2008-04-07 | 2008-04-09
3 | oval works | Run the program and look | 2008-04-07 | 2008-04-10
4 | rectangle can be drawn | Run the program and look | 2008-04-07 | 2008-04-10
5 | paintbrush works | Run the program and look | 2008-04-09 | 2008-04-09
6 | polygon works | Run the program and look | 2008-04-11 | 2008-04-15
7 | can change color from black | Run the program and look | 2008-04-11 | 2008-04-10
8 | extra features | Run the program and look | 2008-04-15 | 2008-04-09 | graffiti can done
9 |  |  |  | 2008-04-15 | undo works
10
11
12
13
14