## Sheet1
Project name: Paint |  | Team number and members: Team 113 - Jenny Kotsybar & Brad Holland
Stage | What the program will do | How we plan to test it | expected completion date | actual completion date
1 | The frame appears on the screen and the layouts for the frame is set up. | Run the program to see if the frame appears. | 2008-04-08 | 2008-04-09
2 | Buttons for the tools (brush, pencil, shapes, and fill) appear in the Frame. | Run the program to see if the buttons appear and are in the correct spot. | 2008-04-08 | 2008-04-09
3 | An ActionListener responds to button the buttons when they are pushed. | Do a print statement to print to the console when the buttons are pressed. | 2008-04-10 | 2008-04-10
4 | A JPanel is created to draw in and added to the right spot in the frame. | Run the program to see if panel appears. | 2008-04-10 | 2008-04-10
5 | A MouseMotionListener responds to mouse motion in the panel to draw in. | Do a print statement to print to the console when the mouse is clicked in the drawing area. | 2008-04-10 | 2008-04-09
6 | A method for the brush button is created so the bursh draws on the drawing area when the button is clicked and the user drags the mouse through the drawing area. | Run the program to see if the method works. | 2008-04-11 | 2008-04-14
7 | A method for the pencil button is created so the pencil draws on the drawing area when the button is clicked and the user drags the mouse through the drawing area. | Run the program to see if the method works. | 2008-04-11 | 2008-04-11
8 | A method to draw a line is created and a line is drawn in the drawing area when the user does so | Run the program to see if the method works. Also, add a print statement to print a line to the console that shows where the shape was drown, so confrim the shape was drawn | 2008-04-11 | 2008-04-08
9 | A method to draw a rectangle is created and a rectangle is drawn in the drawing area when the user does so | Run the program to see if the method works. Also, add a print statement to print a line to the console that shows where the shape was drown, so confrim the shape was drawn | 2008-04-11 | 2008-04-09
10 | A method to draw an oval is created and an oval is drawn in the drawing area when the user does so | Run the program to see if the method works. Also, add a print statement to print a line to the console that shows where the shape was drown, so confrim the shape was drawn | 2008-04-11 | 2008-04-10
11 | A method to draw a polygon is created and a polygon is drawn in the drawing area when the user does so | Run the program to see if the method works. Also, add a print statement to print a line to the console that shows where the shape was drown, so confrim the shape was drawn | 2008-04-11 | 2008-04-10
12 | A color viewer is creared to change the colors. The pallet appears in the correct place in the frame and the user can change colors when they draw something new. | Run the program and see if the color changes when needed. Also, add a print statement to print a line to the console that confirms the color has been changed. | 2008-04-12 | 2008-04-14
13 | When the user holds the shift key down, a perfect square can be drawn from the rectangle method or a perfect circle can be drawn from the oval method. | Run the program and see if the color changes when needed. Also, add a print statement to print a line to the console that confirms the color has been changed. | 2008-04-14 | 2008-04-14
14 | A method for the fill button is created and shapes are filled in when the user draw a shape. | Run the program to see if the method works. | 2008-04-11 | 2008-04-14
15 | Create a File Menu | Run the program to see if the menu functions correctly. | 2008-04-14 | This was optional and we did not get to it.