Project Plan

For a senior project, done in MS-Word

(Different from yours in that it was for a larger project and had more pieces to the plan.)

Team member names went here.

You don't have to use this Word template, by the way. Indeed, Excel is a perfectly valid alternative for this.

3/28/2011

Contents

Process	3

Schedule for Fall Quarter	3

Schedule for Winter Quarter	4

Schedule for Spring Quarter	4

Risks	4

Configuration Management Plan	5

Reference Documents	5

Management	5

Organization and Responsibilities	5

Policies, Directives, and Procedures	5

Build/release schedule	5

Activities	5

Configuration Identification	5

Configuration Control	6

Resources	6

Schedules	6

Resources	7

Plan Maintenance	7

Revision History	7

# Process

The team described how they were going to go about this, using SCRUM, in their case.

# Schedule for Fall Quarter

Their schedule is more general than yours should be - where we'll expect to see some entries for each week!

Everything's shown as done because this was their final version, at the end of the school year.  So naturally they showed everything done for each quarter.

| Task Name | Duration | Start Date | Finish Date | % | Assigned To |
| --- | --- | --- | --- | --- | --- |
| Decide on Process/Lifestyle | 10 Days | 9/17/2010 | 9/27/2010 | 100% | AB, MB, MT, JW |
| Metrics Plan | 5 Days | 9/12/2010 | 9/17/2010 | 100% | AB, JW |
| Preliminary Problem Statement | 7 Days | 9/22/2010 | 9/29/2010 | 100% | MB, MT, JW |
| Preliminary Project Plan | 7 Days | 9/22/2010 | 9/29/2010 | 100% | AB, MT, JW |
| Project Plan | 42 Days | 9/29/2010 | 11/17/2010 | 100% | AB, MB, MT, JW |
| Requirements Document Draft | 14 Days | 9/21/2010 | 10/5/2010 | 100% | AB, MB, MT |
| Week 4 Presentation Prep | 2 Days | 9/27/2010 | 9/29/2010 | 100% | JW |
| Week 4 Presentation | 1 Day | 9/29/2010 | 9/29/2010 | 100% | MT |
| Requirements Document Sign Off | 22 Days | 9/28/2010 | 10/20/2010 | 100% | AB, MB, MT, JW |
| Design/Architecture Document Final | 30 Days | 10/11/2010 | 12/15/2010 | 100% | AB, MB, JW |
| Configuration Management Plan Final | 30 Days | 10/11/2010 | 11/10/2010 | 100% | AB, MB, MT, JW |
| Risk Assessment Final | 10 Days | 10/11/2010 | 10/21/2010 | 100% | AB, MB, MT, JW |
| Maintenance Plan Final | 10 Days | 10/11/2010 | 10/21/2010 | 100% | AB, MB, MT, JW |
| User Interface Prototype | 15 Days | 10/25/2010 | 11/11/2010 | 100% | AB, MB, MT, JW |

# Schedule for Winter Quarter

| Task Name | Duration | Start Date | Finish Date | % | Assigned To |
| --- | --- | --- | --- | --- | --- |
| GUI Screens | 7 Days | 12/1/2010 | 12/8/2010 | 100% | AB, MB, MT, JW |
| GUI Screen Modification | 7 Days | 12/8/2010 | 12/15/2010 | 100% | AB, MB |
| Server Trivia Application | 21 Days | 12/15/2010 | 1/12/2011 | 100% | AB, MB |
| Client Trivia Application | 7 Days | 1/5/2011 | 1/12/2011 | 100% | AB, MB |
| Server/Client Interaction | 7 Days | 1/12/2011 | 2/15/2011 | 90% | MT, JW |
| Other Questions Implemented | 7 Days | 1/19/2011 | 2/11/2011 | 85% | AB, MB, MT, JW |
| Testing | 7 Days | 1/26/2011 | 2/16/2011 | 70% | AB, MB, MT, JW |
| Final Product Deployed | 84 Days | 11/28/2010 | 2/14/2011 | 70% | AB, MB, MT, JW |

# Schedule for Spring Quarter

| Task Name | Duration | Start Date | Finish Date | % | Assigned To |
| --- | --- | --- | --- | --- | --- |
| Multiple Users | 14 Days | 3/7/2011 |  | 70% | MT, JW |
| Fix Question Display for Map and Faded Picture | 7 Days | 3/7/2011 | 5/1/2011 | 100% | MT, JW |
| Code Refactoring | 14 Days | 3/7/2011 |  | 80% | AB, MB, MT, JW |
| Information Screen | 5 Days | 3/7/2011 | 3/12/2011 | 100% | AB, MB |
| System Installer | 14 Days | 4/4/2011 | 4/29/2011 | 100% | AB, MB, MT, JW |
| Bug Fixes | 70 Days | 3/7/2011 |  | 50% | AB, MB, MT, JW |

# Risks

This is the key section we want to talk most about each week.  From our perspective, you should always be working on eliminating some risks, unless the project is done!  As you get to new phases of the project, you should be able to check some of these off, and you also will become aware of new ones, which then need to be listed.

| ID | Type | Probability | Impact | Strategy | Outcome | Resources |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Complications integrating with existing software | Medium | The schedule falls behind | Work closely with Qwarq developers | Prevent complications | Time |
| R2 | Client requests major changes | Low | The schedule falls behind | Continue frequent communication with client discussing progress | Client is able to suggest changes earlier in development | Time |
| R3 | Project is more difficult that estimated | Low | The schedule falls behind | Revise work estimate and schedule | Minimal schedule delay | Time |
| R4 | Lack of interest in games | Low | The project may not be usable | Make use of usability testing to ensure interest | Develop a more interesting game | Time |

# Configuration Management Plan, etc

…This was a bigger plan and they had more sections like this!.  For some of your projects, configuration management is actually a big problem, which deserves some detail.  Like, if you are deploying it on someone else's servers, or on portable devices.  See this team's table of contents for suggested topics.

# Revision History

| Revision | Date | Whom | Changes Made |
| --- | --- | --- | --- |
| 1.0 | 9/30/2010 | The people involved… | All sections of the first draft filed |
| 2.0 | 12/15/2010 |  | Modified descriptions to reflect design changes |
| 3.0 | 2/18/2011 |  | Added and updated schedules |
| 4.0 | 3/28/2011 |  | Updated schedules |
| 5.0 | 5/12/2011 |  | Updated content and schedules |